## PreProduction
| 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-06 | 2019-07-07 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-13 | 2019-07-14 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-20 | 2019-07-21 | 2019-07-22 | 2019-07-23 | 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | Onwards
Concepting
¦_ Game Design
¦_ Narrative | bar: 2019-07-08 to 2019-08-09
¦_ Player Character | bar: 2019-07-08 to 2019-08-09
¦_ Environment | bar: 2019-07-11 to 2019-08-09
¦_ Documentation | bar: 2019-07-13 to 2019-08-09
¦_ User Interface | bar: 2019-07-13 to 2019-08-09
Prototyping
¦_ Mechanics: Player Controller | bar: 2019-07-05 to 2019-07-26
¦_ Mechanics: Gravity Inversion | bar: 2019-07-05 to 2019-08-04
¦_ Mechanics: Time - Slowmo
¦_ Mechanics: Time - Pause
¦_ Mechanics: Blink [up]
¦_ Mechanics: Blink [side]
¦_ Design: Level Design | bar: 2019-07-24 to 2019-08-08
Prototype Build
¦_ Source Files | bar: 2019-08-08 to 2019-08-09
¦_ Game Build | bar: 2019-08-08 to 2019-08-09

## Production
 | time axis 2019-08-09 to 2019-12-16
Level Design:
Paper prototype
Gravity puzzles
Time slow puzzles
Time stop puzzles
Teleportation puzzles
Hybrid puzzles
Level test implementation
Narrative:
Narrative breakdown
Andy backstory
Ryan (creator) backstory
Jason (evil scientist) backstory
Dialogue scripting (actual dialogue)
Narrative scripting (event based code)
Diagetic narrative planning
Tutorial creation
Mechanics:
Interactable (doors, moving platforms, etc)
Gravity
Time slow
Time stop
Teleportation
Object selection (modularity; one selection to control all abilities)
Pick-up objects
Testing:
Player gravity testing
Other/global gravity testing
Time slow testing
Time stop testing
Teleportation testing
Level testing
Kleenex Tests
Control mapping testing
Tutorial testing
Narrative flow testing
Level testing

## Final
 | time axis 2019-07-03 to 2019-12-16